## Sheet1
MRGBAD001 Undergraduate Thesis Plan
Activity | Description | Planned Start Date | Planned End Date | Actual Start Date | Changes | Reason for Delay | Actual End Date | Estimated Percent Completed
Column1 | Column2 | Column3 | Column4 | Column5 | Column53 | Column52 | Column6 | Column7
Planning
Simplifying Project Defintion | Further define the project so it is clearer to see what direction to take, will finish as specified but continuous updates will be required | 2016-07-18 | 2016-07-22 | 2016-07-18 |  |  | 2016-07-22 | 90%
Gantt chart | Project plan detailing each activity with its start and end date, will finish as expected but continuous updates will be required | 2016-07-20 | 2016-07-29 | 2016-07-20 | changed end date to accomedate Further Continues Assessment | Sick |  | 20%
Design and Report
Design modular pcb | design pcb that can accommodate all eventual | 2016-07-26 | 2016-07-29 | 2016-07-26 | everything got pushed back one day because of being sick
Initialize document | Create Document to start working on for report | 2016-07-26 | 2016-07-28 | 2016-07-26
Litariture review | Critical review of papers and reports on similar material to this report, will be ongoing | 2016-07-26 | 2016-08-26 |  |  | sick and too many things were strarted on this day
Review Pcb | check that the layout is correct and send to peers to review | 2016-07-30 | 2016-07-30
Design Delivery Mechanism:
Vertical wheel |  | 2016-07-27 | 2016-07-29
Horizontal Wheel |  | 2016-07-28 | 2016-07-30
Other Design |  | 2016-07-29 | 2016-07-31
Testing
Test Delivery Mechanisms | Test the reliability of the delivery mechanisms | 2016-08-03 | 2016-08-07
Theoretical Enclosure design | Theoretical design as the final design will be based on this however will need to accomidate the project as it stands when an enclosure is needed